## Instructions
UW Green Building Standard Workbook
| for tracking and reporting on compliance | [5 empty] | EP status
Workbook contents:
The tabs in this workbook are color coded to match the steps in the process below.
2/14 - Have reviewed and edited top two categories in all Tiers
How to use this workbook: | [6 empty] | 2/19 - Step 3 - Tiers 4 and 3 are done (for now). Tier 2b in progress.
| Project Formation - CAP |  |  |  | Execution - PDG
| Project Initiation |  |  | Project Development
How to fill out the worksheets:
Cells filled with grey are not applicable and do not need to be filled out.
Cells requiring a yes or no answer have drop downs with "Y" and "N" choices.
Guidance for completing each open cell is in grey. Replace with project specifics.
Based on the response provided in open cells, indicate status in the adjacent cells that have a drop down and formatting like this:
| On track |  | Complies
| Still in development | or this: | Does not comply
Off track
CAP
Start here - Make a copy of this workbook file and add it to project files
Answer the 'yes-no' questions in the Step 1 worksheet to confirm the GBS is applicable to the project.
Applicable?
Answer the 'yes-no' questions in the Step 2 worksheet to confirm the GBS Tier applicable to the project.
Go to the Step 3 worksheet for the appropriate Tier and determine the applicable requirements.
Continue to use the Step 3 worksheet for tracking and reporting on GBS compliance for the remainder of the project.
Report on GBS compliance at project milestones listed in the workbook
You may delete Step 3 worksheets for tiers not applicable to the project. To delete worksheets, under the Review tab for the worksheet, select "Manage Protection". Then turn the "Protect sheet" to off; right-click on the tab and select "delete"
Yes
Requirements?
If not applicable, save this workbook in the project file as a record of the result.
No
If there are no applicable requirements, save this workbook to the project file as a record of the result.
No
Yes
Submit a copy of the workbook and any required documentation to UW Sustainability at greenbuildings@uw.edu

## Step 1 - Confirm Applicability
PHASE: Project Formation
SUBPHASE: Project Initiation
GBS Applicability
| Question | Y/N | If Yes | If No | Notes
a | Is this a capital project (see Notes)? |  | Continue to question b. | GBS is N/A, stop here. | Exclude maintenance projects, "planning" projects where capital dollars are being used for planning (e.g. a MIMP) or studies, commissioning, "patch and paint," and equipment used by staff to do the job (e.g. safety radios).
b | Is the budget $1,000,000 or greater? |  | Continue to question c. | GBS is N/A, stop here.
c | Is it in Washington State? |  | Continue to question d. | GBS is N/A, stop here.
d | Is it for a property that is owned and operated by the UW? |  | Continue to question e. | GBS not currently applicable, stop here. | These project will have GBS requirements when Phase 2 is launched.
e | Did/will the project complete project formation after June 30, 2024? |  | GBS v2 is applicable. Proceed to step 2. | GBS v2 is not required. GBS v1 may apply. | Projects required to do GBS v1 must work with UW Sustainability to agree on GBS v2 elements to incorporate into the project wherever possible.

## Step 2 - Determine Tier
PHASE: Project Formation
SUBPHASE: Project Initiation
Tier Identification
|  | Y/N | If Yes | If No | Notes
a | Is this project new construction or major renovation of a whole building or stand alone addition? |  | Project is Tier 1, proceed to question f and enter Tier 1 as the answer. | Continue to question b.
b | Is the project upgrading or adding new mechanical, electrical, or plumbing equipment or systems that consume or influence consumption of energy or water (see Notes)? |  | Continue to question c. | Go to question e. | e.g. applies to fume hoods and elevators, but not to switch gear, applies to elevator modernization, but not door upgrades with LV controls. Applies to distribution or controls projects where options directly influence energy consumption. Exclude low voltage technology and fire safety systems.
c | Is there additional project scope on the building structure or finishes beyond direct impacts of the system upgrade? |  | Project may be Tier 2, continue to question 'd' to distinguish between 2a and 2b. | Project is Tier 3, proceed to question f and enter Tier 3 as the answer.
d | Is the project eligible for LEED v4 Commercial Interiors certification? |  | Project is Tier 2a, proceed to question f and enter Tier 2a as the answer. | Project may be Tier 2b continue to question e.
e | Is the project comprised of any materials where the Carbon Leadership Forum has established embodied carbon baselines in its most current baseline report (see Notes)? |  | Projects that said "Y" to question b, are Tier 2b, proceed to question f and enter Tier 2b as the answer. Projects that said "N" to question b are Tier 4, proceed to question f and enter Tier 4 as the answer. | No applicable GBS requirements, stop here. | - Refer to definitions of materials in CLF baseline report - Where there are no applicable GBS requirements, the GBS is not applicable to the project.
f | What Tier is the project? Answering the questions above will help you determine this; als see 'Definitions' and 'Decision Tree' below.
Tier Definitions
Description
Tier 1 | New construction and major renovation | New ground up construction, major renovations of whole buildings and stand-alone additions.
Tier 2a | Partial building renovations | Projects that include multiple system upgrades or renovations (HVAC, plumbing, lighting, finishes) and that have distinct, contiguous space eligible for LEED v4 certification.
Tier 2b | Interiors projects | Projects that include multiple system upgrades or renovations (HVAC, plumbing, lighting, finishes). Scope may be distributed throughout a building, not eligible for LEED v4 certification.
Tier 3 | System upgrades | Projects that are upgrading or adding new mechanical, electrical, and plumbing equipment or systems that will consume or influence the University's consumption of energy or water and that do not include additional scope.
Tier 4 | Non-energy projects | Non-energy projects involving materials but limited or no systems.
Tier Decision Tree

## Step 3 - Tier 4 Track & Report
Tier 4 GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project. Guidance for completing each open cell is in grey. Replace with project specifics. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that subphase. | PHASE: Project Formation |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  | SUBPHASE: Early Design Milestone |  | SUBPHASE: Close out
|  | Applicable? | Initial Project Approach | On track? | Confirm Project Approach | On track? | Report Project Results | Completed? | Required documentation
PROCESS | Follow UW GBS Process - applicable to all Tier 4 projects. | Y | 1) Complete this column at the end of project formation and submit to UW Sustainability. 2) Allow 10 days for comments or responses. |  | 1) Complete this column at an early design milestone and submit to UW Sustainability. 2) Allow 10 days for comments or responses. |  | 1) Complete this column at the end of the project and collect required documentation. 2) Submit to UW Sustainability with required documentation. |  | N/A
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments (applicable to all Tier 4 projects). | Y | Track any variances from UW standards separately. |  | N/A |  | N/A |  | N/A
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components? |  | Identify opportunities for conserving water on the project. |  | Confirm project approach to water conservation and estimate water saving |  | Confirm water conservation measures included and estimated water savings. |  | Back up calculations for estimated energy savings through water conservation.
EMBODIED CARBON | Product embodied carbon limits - For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit (applicable to all Tier 4 projects). | Y | List likely applicable materials in the project. Indicate any other strategies used that reduce the carbon footprint. |  | List confirmed applicable materials and the kgCO2e per declared unit limit. |  | List applicable materials used on the project and the kgCO2e per declared unit . |  | Submit EPDs for applicable materials.
HEALTH AND WELL-BEING | Are there opportunities to include features and materials that support health and well-being in this project? |  | Indicate any opportunities for the project that support health and well-being. |  | Indicate strategies planned for the project that support health and well-being. |  | Confirm strategies included in the project that support health and wellbeing. |  | No additional documentation required.
EQUITY | Are there opportunities to include features and materials that support equity in this project? |  | Indicate any opportunities for the project that support equity. |  | Indicate strategies planned for the project that support equity. |  | Confirm strategies included in the project that support equity. |  | No additional documentation required.
|  |  | Project Development Result | On Track | Early Design Milestone Result | Still in development | Close out Result
|  |  | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | Complies
| Materials with embodied carbon limits in 2023 CLF North American Material Baselines Report |  |  | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Any No (red) | Does not comply
| - concrete or masonry |  | Any No (red) | Off track | Any No (red) | Off track
- steel
- aluminum
- wood framing, composite lumber, or mass timber
- insulation
- metal panel cladding (not insulated)
- membrane roofing
- flat glass (not IGUs)
- gypsum board (lightweight, type X, and glass mat)
- resilient vinyl or rubber flooring

## Step 3 - Tier 3 Track & Report
Tier 3 GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project. Guidance for completing each open cell is in grey. Replace with project specifics. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that phase. | PHASE: Project Formation |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  | SUBPHASE: Early Design Milestone |  | SUBPHASE: Close out
|  | Applicable? | Initial Project Approach | On track? | Confirm Project Approach | On track? | Report Project Results | Complete? | Required documentation
PROCESS | Follow UW GBS Process - applicable to all Tier 3 projects. | Y | 1) Complete this column at the end of project formation and submit to UW Sustainability. 2) Allow 10 days for comments or responses. |  | 1) Complete this column at an early design milestone and submit to UW Sustainability. 2) Allow 10 days for comments or responses. |  | 1) Complete this column at the end of the project and collect required documentation. 2) Submit to UW Sustainability with required documentation. |  | N/A
LIFE CYCLE COST ANALYSIS | UW LCCA requirements - does project meet definition of major or minor project in the UW LCCA Requirements? |  | Indicate what options or systems the LCCA will evaluate. |  | Summarize results of LCCA. Provide report as documentation. | No | N/A |  | LCCA Results.
| State ELCCA - Does the state funding require ELCCA on this project? |  | N/A |  | 1) Confirm State required ELCCA workplan submited to the state. 2) Complete EELCCA by mid-design milestone and submit to the state. |  | N/A |  | ELCCA Report.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments - applicable to all Tier 3 projects. | Y | Track any variances from UW standards separately |  | N/A |  | N/A |  | No documentation required.
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate plans for connecting to district energy. |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  | Confirm use(s) of fossil fuels on the project and estimated annual fossil fuel use. |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA maybe necessary to justify keeping or adding fossil fuels. |  | Confirm project is on track for connecting to district energy. |  | Confirm district energy connection made. |  | No additional documentation required.
| Energy conservation measures - Are there opportunities to use different or more efficient systems or equipment or otherwise save energy on the project (ECMs)? |  | Summarize opportunities for energy conservation. |  | Indicate energy conservation measures planning to include in the project and estimated energy savings. |  | Confirm energy conservation measures included and estimated energy savings. |  | Back up calculations for estimated energy savings through energy conservation.
| Energy Use Intensity (EUI) Targets (EUIt): Does the project include substantial modification to the mechanical and electrical systems, meeting the definition for minor renovation in the UW LCCA requirements and/or is the project located in Seattle and not connecting to the district energy system? |  | Calculate EUIt and GHGi target by activity for the affected spaces per CBPS, and BEPS if applicable. |  | Provide the project's estimated EUI, and GHGi if applicable. |  | Provide the project's final EUI, and GHGi if applicable. |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS or other University standards? |  | Identify water consuming fixtures, appliances, or equipment with their efficiency requirement. |  | Confirm water consuming fixtures, appliances, and equipment planned for the project meets or exceeds efficiency standards. |  | List water consuming fixtures, appliances, and equipment used in the project and their efficiency. Confirm they all meet or exceed standard. |  | No additional documentation required.
| Supporting low-flow fixtures - is the project upgrading plumbing and/or replacing drainlines? |  | Indicate if there are applicable opportunities to address barriers to low-flow fixture installation or performance. |  | Describe any improvements to support low flow fixtures planned for the project. |  | Confirm improvements to support low flow fixtures included in the project. |  | No additional documentation required.
EMBODIED CARBON | Embodied carbon reporting requirements are not applicable to Tier 3 projects. Project teams are encouraged to investigate the latest information available on embodied carbon in systems and equipment and consider how to reduce embodied carbon. Answer yes, "Y", if opportunities to reduce embodied carbon are available. |  | Indicate any opportunities in the project that reduce embodied carbon. |  | Indicate strategies planned for in the project that reduce embodied carbon and estimated reduction. |  | Confirm strategies included in the project that reduced embodied carbon and the estimated reduction. |  | No additional documentation required.
HEALTH AND WELL-BEING | Are there opportunities to include features and materials that support health and well-being in this project? |  | Indicate any opportunities for the project that support health and well-being. |  | Indicate strategies planned for the project that support health and well-being. |  | Confirm strategies included in the project that support health and wellbeing. |  | No additional documentation required.
EQUITY | Are there opportunities to include features and materials that support equity in this project? |  | Indicate any opportunities for the project that support equity. |  | Indicate strategies planned for the project that support equity. |  | Confirm strategies included in the project that support equity. |  | No additional documentation required.
|  |  | Project Development Result |  | Early Design Milestone Result |  | Close out Result
|  |  | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Any No (red) | Does not comply
|  |  | Any No (red) | Off track | Any No (red) | Off track

## Step 3 Tier 2b Track and Report
Tier 2b GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project. Guidance for completing each open cell is in grey. Replace with project specifics. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that phase. | PHASE: Project Formation |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  | SUBPHASE: Early Design Milestone |  | SUBPHASE: Close out
|  | Applicable? | Initial Project Approach | On track? | Confirm Project Approach | On track? | Report Project Results | Complete? | Required documentation
PROCESS | Follow UW GBS Process - applicable to all Tier 2b projects. | Y | 1) Complete this column (below) at the end of project formation and submit to UW Sustainability. 2) Allow 10 days for comments or responses. |  | 1) Complete this column at an early design milestone and submit to UW Sustainability 2) Allow 10 days for comments or responses |  | 1) Complete this column at the end of the project and collect required documentation. 2) Submit to UW Sustainability with required documentation |  | N/A
LIFE CYCLE COST ANALYSIS | UW LCCA requirements - does project meet definition of major or minor project in the UW LCCA Requirements? |  | Indicate what options or systems the LCCA will evaluate. |  | Summarize results of LCCA. Provide report as documentation. |  | N/A |  | LCCA Report
| State ELCCA - Does the state funding require ELCCA on this project? |  | N/A |  | 1) Confirm State required ELCCA workplan submited to the state. 2) Complete EELCCA by mid-design milestone and submit to the state. |  | N/A |  | ELCCA Report.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 2b projects. | Y | Track any variances from UW standards separately |  | Track any variances related to the GBS in variance log |  | Confirm all related variances closed out
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA maybe necessary to justify keeping or adding fossil fuels. |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  | Confirm use(s) of fossil fuels on the project and estimated annual fossil fuel use. |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate plans for connecting to district energy. |  | Confirm project is on track for connecting to district energy. |  | Confirm district energy connection made. |  | No additional documentation required.
| Energy conservation measures - Are there opportunities to use different or more efficient systems or equipment or otherwise save energy on the project (ECMs)? |  | Summarize opportunities for energy conservation. |  | Indicate energy conservation measures planning to include in the project and estimated energy savings. |  | Confirm energy conservation measures included and estimated energy savings. |  | Back up calculations for estimated energy savings through energy conservation.
| Energy Use Intensity (EUI) Targets (EUIt): Does the project include substantial modification to the mechanical and electrical systems, meeting the definition for minor renovation in the UW LCCA requirements and/or is the project located in Seattle and not connecting to the district energy system? |  | Calculate EUIt and GHGi target by activity for the affected spaces per CBPS, and BEPS if applicable, and list results here. |  | Confirm the applicable target(s) Provide the estimated EUI, and GHGi if appliacable, for the affected spaces in the project. |  | Provide the final EUI, and GHGi if applicable, for the affected spaces. |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS or other University standards? |  | Identify water consuming fixtures, appliances, or equipment with their efficiency requirement. |  | Confirm water consuming fixtures, appliances, and equipment planned for the project meets or exceeds efficiency standards. |  | List water consuming fixtures, appliances, and equipment used in the project and their efficiency. Confirm they all meet or exceed standard. |  | No additional documentation required.
| Supporting low-flow fixtures - is the project upgrading plumbing and/or replacing drainlines? |  | Indicate if there are applicable opportunities to address barriers to low-flow fixture installation or performance. |  | Describe any improvements to support low flow fixtures planned for the project. |  | Confirm improvements to support low flow fixtures included in the project. |  | No additional documentation required.
EMBODIED CARBON | Product embodied carbon limits - For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. Applicable to all Tier 2b projects. | Y | List likely applicable materials in the project. Indicate any other strategies used that reduce the carbon footprint. |  | List confirmed applicable materials and the kgCO2e per declared unit limit. |  | List applicable materials used on the project and the kgCO2e per declared unit . |  | Submit EPDs for applicable materials.
RATING SYSTEM | Opportunity for LEEDv4.1 O+M - Does the scope of this project improve overall energy efficiency of the building? |  | Work with the LEED UW Admin and UW Sustainability to evaluate LEEDv4.1 O+M Gold certification. |  | Confirm if the building will pursue LEEDv4.1 O+M Gold when the project is complete. Summarize plans to prepare the building via design and construction of the project. |  | Confirm project included any design and construction necessary to support LEEDv4.1 O+M Gold certification. |  | Preliminary LEEDv4.1 O+M Gold scorecard.
| Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 2b projects. | Y | List Fitwel v3 credits under evaluation. |  | Confirm Fitwel v3 credit planned to pilot. |  | Indicate the Fitwel credit pursued. |  | Fitwel v3 credit documentation.
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include alterations to the building envelope? |  | Identify the applicable UW Bird-Friendly Design Guidelines. |  | Confirm the UW Bird-Friendly Design Guidelines planned for the project. |  | Confirm the UW Bird-Friendly Design Guidelines included in the project. |  | No additional documentation required.
HEALTH AND WELL-BEING | Showers and changing facilities - Is there an opportunity for this project to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being in this project? |  | Describe opportunities to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being. |  | Confirm plans for added or improved showers and changing facilities or other health and well-being strategies. |  | Confirm added or improved showers and changing facilities or other health and well-being strategies included in the project. |  | No additional documentation required.
EQUITY | Lactation facilities - Is there an opportunity for this project to add or improve lactation facilities for staff or to include other features that support equity on this project. |  | Describe opportunities to add or improve lactation facilities for staff or to include other features that support equity. |  | Confirm plans for added or improved lactation facilities or other equity strategies. |  | Confirm added or improved lactation facilities or other equity strategies included in the project. |  | No additional documentation required.
| UW Gender-Neutral Restroom policy - are restrooms being added or improved as part of this project? |  | Follow UW Gender Neutral Restroom policy. Track any variances with other project variances. |  | N/A |  | N/A |  | No additional documentation required.
|  |  | Project Development Result |  | Early Design Milestone Result |  | Close out Result
|  |  | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Any No (red) | Does not comply
|  |  | Any No (red) | Off track | Any No (red) | Off track
1) Prepare State required LCCA workplan at early design milestone and submit to the state.
2) Complete LCCA by mid-design milestone and submit to the state.

## Step 3 Tier 2a Track and Report
Tier 2a GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project. Guidance for completing each open cell is in grey. Replace with project specifics. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that phase. | PHASE: Project Formation | [5 empty] | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  | SUBPHASE: Project Definition |  | SUBPHASE: Early Design Milestone |  | SUBPHASE: Mid Design Milestone |  | SUBPHASE: Post 100% Design Milestone |  | SUBPHASE: Close out
|  | Applicable? | Initial Project Approach | On track? | Confirm Project Approach | On track? | Confirm Project Approach | On track? | Confirm Project Approach | On track? | Confirm Project Approach | On track? | Report Project Results | Complete? | Required documentation
PROCESS | Follow UW GBS Process - applicable to all Tier 2a projects. | Y | 1) Complete this column at the end of project formation. 2) Include plans for GBS compliance and LEED certification in pre-design report or other project development documentation. 3) Submit workbook and project development documentation to UW Sustainability. 4) Allow 10 days for comments or responses. |  | 1) Complete this column at the end of project definition. 2) Report results of analyses and plans for GBS compliance and LEED certification in project definition deliverable. 3) Submit workbook and project definition documentation to UW Sustainability. 4) Schedule a meeting to review with UW Sustainability. |  | 1) Complete this column at an early design milestone. 2) Include plans for GBS compliance and LEED certification in early design milestone deliverable. 3) Submit workbook and project milestone documentation to UW Sustainability. 4) Allow 10 days for comments or responses. |  | 1) Complete this column at an mid-design milestone. 2) Include plans for GBS compliance and LEED certification in mid-design milestone deliverable. 3) Submit workbook and project milestone documentation to UW Sustainability. 4) Allow 10 days for comments or responses. |  | 1) Within 90 days of substantial completion: a) Complete this column. b) Complete and quality check all design-phase LEED documentation in LEED Online. 2) Submit workbook to UW Sustainability. 3) Allow 10 days for comments or responses. 4) Notify UW LEED Admin that documentation is ready for review 5) Complete and accept LEED Final Design Review with 180 days of 100% design. |  | 1) Within 90 days of substantial completion: a) Complete this column. b) Complete and quality check all construction-phase LEED documentation in LEED Online, except for commissioning documentation. 2) Submit workbook to UW Sustainability. 3) Notify UW LEED Admin that documentation is ready for review. 4) Allow 10 days for comments or responses 5) Address UW and GBCI review comments in a timely manner. |  | As indicated below.
LIFE CYCLE COST ANALYSIS | UW LCCA requirements - does project meet definition of major or minor project in the UW LCCA Requirements? |  | Indicate what options or systems the LCCA will evaluate. |  | Confirm LCCA submitted to CEUO. Provide report as documentation. |  | N/A |  | N/A |  | N/A |  | N/A |  | LCCA Report.
| State ELCCA - Does the state funding require ELCCA on this project? |  | N/A |  | N/A |  | Confirm State required ELCCA workplan submited to the state. |  | Confirm ELCCA complete and submitted to the state. |  | N/A |  | N/A |  | ELCCA Workplan copy.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments - applicable to all Tier 2a projects. | Y | Track any variances from UW standards separately |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA maybe necessary to justify keeping or adding fossil fuels. |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  | N/A |  | N/A |  | Confirm use(s) of fossil fuels on the project and estimated annual fossil fuel use. |  | N/A |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate plans for connecting to district energy. |  | Confirm project is on track for connecting to district energy. |  | N/A |  | N/A |  | Confirm district energy connection made. |  | N/A |  | No additional documentation required.
| Energy conservation measures - Are there opportunities to use different or more efficient systems or equipment or otherwise save energy on the project (ECMs)? |  | Summarize opportunities for energy conservation. |  | N/A |  | Indicate energy conservation measures planned for inclusion in the project. |  | Update any changes to projects planned ECMs. |  | Confirm energy conservation measures included in the project.Document energy savings in LEED energy model as applicable. |  | N/A |  | No additional documentation required.
| Energy Use Intensity (EUI) Targets (EUIt): Does the project include substantial modification to the mechanical and electrical systems, meeting the definition for minor renovation in the UW LCCA requirements and/or is the project located in Seattle and not connecting to the district energy system? |  | Calculate EUIt and GHGi target by activity for the affected spaces per CBPS and BEPS and indicate the results here. |  | Confirm the applicable target(s) with any changes in area of use of spaces. |  | Provide the estimated EUI, and GHGi if appliacable, for the affected spaces in the project showing compliance with the targets. |  | N/A |  | Provide the final EUI, and GHGi if applicable, for the affected spaces. |  | N/A |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS? |  | Identify likely water consuming fixtures, appliances, or equipment. |  | Confirm water consuming fixtures, appliances, and equipment planned for the project and their efficiency standards. |  | Confirm water consuming fixtures, appliances, and equipment planned for the project meet or exceed efficiency standards. |  | N/A |  | N/A |  | N/A |  | No additional documentation required.
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED ID+C v4 baseline unless existing plumbing will not support lower flow. |  | Indicate required percent reduction here. |  | Perform preliminary water savings calculations to plan which fixtures and which flow rates to include in the project. Confirm if on-track. |  | Update or confirm project on-track |  | N/A |  | Document water and energy savings from final fixtures, appliances, and equipment selected in the LEED energy model and water calculations as applicable. |  | N/A |  | Documented with LEED credit documentation. Compiled by UW LEED Admin.
EMBODIED CARBON | Product embodied carbon limits - For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. Applicable to all Tier 2a projects. | Y | List likely applicable materials in the project. |  | Update list of likely applicable materials in the project and the kgCO2e per declared unit limit. |  | N/A |  | Include low-carbon materials requirements and the kgCO2e per declared unit limit in specifications. |  | N/A |  | List applicable materials used on the project and the actual kgCO2e per declared unit . |  | Submit EPDs for applicable materials.
| At the end of the project, report as-built embodied carbon of actual new construction materials using the EC3 tool and following the LEED pilot credit for Procurement of Low-Carbon Construction Materials (MRpc132). Applicable to all Tier 2a projects. | Y | N/A |  | N/A |  | N/A |  | Require submittal of EPDs showing kgCO2 per declared unit in specification for all materials in the LEED credit |  | N/A |  | Complete calculation following the LEED pilot credit. List total embodied carbon footprint baseline and actual here. |  | Documented with LEED credit documentation. Compiled by UW LEED Admin.
RATING SYSTEM | Target LEED CI Gold and earn required credits in the UW LEED CI scorecard, including one innovation or pilot credit from the preferred list. Applicable to all Tier 2a projects. | Y | Create preliminary LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points For exceptions of individual required LEED credits that are unachievable due to project constraints outside of the project team’s ability to influence, provide supporting documentation to the Director of Sustainability and demonstrating how the project will otherwise meet the LEED certification requirement. |  | Update LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard and complete project team responsibilities for LEED design phase review. Perform a QC review and submit to the UW LEED Admin for backcheck within 90 days of 100% design. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points is exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard and complete project team responsibilities for LEED construction phase review. Perform a QC review and submit to the UW LEED Admin for backcheck within 90 days of substantial completion. |  | Documented with LEED credit documentation. Compiled by UW LEED Admin.
| Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 2a projects. | Y | List Fitwel v3 credits under evaluation. |  | Confirm Fitwel v3 credit planned to pilot. |  | N/A |  | N/A |  | Indicate the Fitwel credit pursued. |  | N/A |  | Fitwel v3 credit documentation.
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include alterations to the building envelope? |  | Identify the applicable UW Bird-Friendly Design Guidelines. |  | Confirm the UW Bird-Friendly Design Guidelines planned for the project. |  | N/A |  | N/A |  | Confirm the UW Bird-Friendly Design Guidelines included in the project. |  | N/A |  | No additional documentation required.
HEALTH AND WELL-BEING | Showers and changing facilities - Is there an opportunity for this project to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being in this project? |  | Describe opportunities to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being. |  | Confirm plans for added or improved showers and changing facilities or other health and well-being strategies. |  | N/A |  | N/A |  | Confirm added or improved showers and changing facilities or other health and well-being strategies included in the project. |  | N/A |  | No additional documentation required.
EQUITY | Lactation facilities - Is there an opportunity for this project to add or improve lactation facilities for staff or to include other features that support equity on this project. |  | Describe opportunities to add or improve lactation facilities for staff or to include other features that support equity. |  | Confirm plans for added or improved lactation facilities or other equity strategies. |  | N/A |  | N/A |  | Confirm added or improved lactation facilities or other equity strategies included in the project. |  | N/A |  | No additional documentation required.
| UW Gender-Neutral Restroom policy - are restrooms being added or improved as part of this project? |  | Follow UW Gender Neutral Restroom policy. Track any variances with other project variances. |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | No additional documentation required.
|  |  | Project Development Result |  | Project Definition Milestone Result |  | Early Design Milestone Result |  | Mid Design Milestone Result |  | Mid Design Milestone Result |  | Close out Result
|  |  | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Any No (red) | Does not comply
|  |  | Any No (red) | Off track | Any No (red) | Off track | Any No (red) | Off track | Any No (red) | Off track | Any No (red) | Off track

## Step 3 Tier 1 Track and Report
Tier 1 GBS Tracking and Reporting |  | PHASE: Project Formation |  |  |  |  | PHASE: Project Execution
Instructions: Complete each column at the end of the corresponding Project Subphase of the project. Guidance for completing each open cell is in grey. Replace with project specifics. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that phase. |  | SUBPHASE: Project Initiation | SUBPHASE: Project Development |  | SUBPHASE: Project Definition |  | SUBPHASE: Early Design Milestone |  | SUBPHASE: Mid Design Milestone |  | SUBPHASE: Post 100% Design Milestone |  | SUBPHASE: Close out
|  | Applicable? | Initial Project Approach | On track? | Confirm Project Approach | On track? | Update on Project Approach | On track? | Update on Project Approach | On track? | Update on Project Approach | On track? | Report Project Results | Complete? | Required documentation
PROCESS | Follow UW GBS Process - applicable to all Tier 1 projects. | Y | 1) Complete this column at the end of project formation. 2) Include plans for GBS compliance and LEED certification in pre-design report or other project development documentation. 3) Submit workbook and project development documentation to UW Sustainability. 4) Allow 10 days for comments or responses. |  | 1) Complete this column at the end of project definition. 2) Report results of analyses and plans for GBS compliance and LEED certification in project definition deliverable. 3) Submit workbook and project definition documentation to UW Sustainability. 4) Schedule a meeting to review with UW Sustainability. |  | 1) Complete this column at an early design milestone. 2) Include plans for GBS compliance and LEED certification in early design milestone deliverable. 3) Submit workbook and project milestone documentation to UW Sustainability. 4) Allow 10 days for comments or responses. |  | 1) Complete this column at an mid-design milestone. 2) Include plans for GBS compliance and LEED certification in mid-design milestone deliverable. 3) Submit workbook and project milestone documentation to UW Sustainability. 4) Allow 10 days for comments or responses. |  | 1) Within 90 days of substantial completion: a) Complete this column. b) Complete and quality check all design-phase LEED documentation in LEED Online. 2) Submit workbook to UW Sustainability. 3) Allow 10 days for comments or responses. 4) Notify UW LEED Admin that documentation is ready for review 5) Complete and accept LEED Final Design Review with 180 days of 100% design. |  | 1) Within 90 days of substantial completion: a) Complete this column. b) Complete and quality check all construction-phase LEED documentation in LEED Online, except for commissioning documentation. 2) Submit workbook to UW Sustainability. 3) Notify UW LEED Admin that documentation is ready for review. 4) Allow 10 days for comments or responses 5) Address UW and GBCI review comments in a timely manner. |  | As indicated below.
LIFE CYCLE COST ANALYSIS | Apply UW LCCA requirements |  | Indicate what options or systems the LCCA will evaluate. |  | Confirm LCCA submitted to CEUO. Provide report as documentation. |  | N/A |  | N/A |  | N/A |  | N/A |  | LCCA Report.
| State ELCCA |  | N/A |  | N/A |  | Confirm State required ELCCA workplan submited to the state. |  | Confirm ELCCA complete and submitted to the state. |  | N/A |  | N/A |  | ELCCA Workplan copy, if required.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 1 projects. | Y | Track any variances from UW standards separately |  | Track any variances related to the GBS in variance log |  | Track any variances related to the GBS in variance log |  | Track any variances related to the GBS in variance log |  |  |  | Confirm all related variances closed out
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA maybe necessary to justify keeping or adding fossil fuels. |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  | N/A |  | N/A |  | Confirm use(s) of fossil fuels on the project and estimated annual fossil fuel use. |  | N/A |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate plans for connecting to district energy. |  | Confirm project is on track for connecting to district energy. |  | N/A |  | N/A |  | Confirm district energy connection made. |  | N/A |  | No additional documentation required.
| Energy Use Intensity (EUI) targets (EUIt): Design the building to perform better than the Washington State Clean Buildings Performance Standard (CBPS) EUIt for the building type and activities. Projects located in Seattle and not connected to the Seattle campus district energy system must also plan for compliance with the City of Seattle Building Performance Standard (BEPS) Greenhouse Gas Intensity (GHGi) target. Applicable to all Tier 1 projects. | Y | Calculate EUIt and GHGi target for the building per CBPS, and BEPS if applicable, and indicate the results here. |  | Confirm the applicable target(s) with any changes in area. |  | Provide the estimated EUI, and GHGi if appliacable, for the building showing compliance with the targets. |  | N/A |  | Provide the final EUI, and GHGi if applicable, for the building. |  | N/A |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS? |  | Identify likely water consuming fixtures, appliances, or equipment. |  | Confirm water consuming fixtures, appliances, and equipment planned for the project and their efficiency standards. |  | Confirm water consuming fixtures, appliances, and equipment planned for the project meet or exceed efficiency standards. |  | N/A |  | N/A |  | N/A |  | No additional documentation required.
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. |  | Indicate required percent reduction here. |  | Perform preliminary water savings calculations to plan which fixtures and which flow rates to include in the project. Confirm if on-track. |  | Update or confirm project on-track |  | N/A |  | Document water and energy savings from final fixtures, appliances, and equipment selected in the LEED energy model and water calculations as applicable. |  | N/A |  | Documented with LEED credit documentation. Compiled by UW LEED Admin.
EMBODIED CARBON | Product embodied carbon limits: For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. |  | List likely applicable materials in the project. |  | Update list of likely applicable materials in the project and the kgCO2e per declared unit limit. |  | N/A |  | Include low-carbon materials requirements and the kgCO2e per declared unit limit in specifications. |  | N/A |  | List applicable materials used on the project and the actual kgCO2e per declared unit . |  | Submit EPDs for applicable materials.
| Identify strategies to reduce the embodied carbon of the project and perform calculations to set a project-specific as-designed total embodied carbon target. Do not exceed the total embodied carbon limit of 500 kgCO2e/m2. Applicable to all Tier 1 projects. | Y | N/A |  | Determine the expected total project as-designed embodied carbon using a life cycle assessment(LCA) tool. Indicate the project-specific total as-designed embodied carbon target. Identify strategies to reduce the embodied carbon. |  | N/A |  | N/A |  | N/A |  | N/A |  | Output report from the LCA for the as-designed total embodied carbon. If project pursues LEED credit for Whole Building Life Cycle Assessment, LEED credit documentation compiled by UW LEED Admin suffices for documentation.
| Is this project a major renovation of an existing building? If so, estimate the embodied carbon impact of the materials required to build a new, similar building using EC3 and the LEED pilot credit (MRpc132) methodology. |  | N/A |  | N/A |  | N/A |  | N/A |  | Prepare the calculation of the embodied carbon impact of the materials required to build a new similar building using EC3 and the LEED pilot credit (MRpc132). Indicate total footprint here. |  | N/A |  | EC3 report with total embodied carbon footprint of a new, similar building.
| At the end of the project, report as-built embodied carbon of actual new construction materials using the EC3 tool and following the LEED pilot credit for Procurement of Low-Carbon Construction Materials (MRpc132). Applicable to all Tier 1 projects. | Y | N/A |  | N/A |  | N/A |  | Require submittal of EPDs showing kgCO2 per declared unit in specification for all materials in the LEED credit |  | N/A |  | Complete calculation following the LEED pilot credit. List total embodied carbon footprint baseline and actual here. |  | EC3 report showing baseline and actual embodied carbon footprint of new materials used on the project. If the project pursues Procurement of Low-Carbon Construction Materials (MPpc132) LEED credit documentation suffices for documentation.
RATING SYSTEM | Earn LEED v4 NC Gold certification including required credits in the UW LEED scorecard, and one innovation or pilot credit from the preferred list. Applicable to all Tier 1 projects. | Y | Create preliminary LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points For exceptions of individual required LEED credits that are unachievable due to project constraints outside of the project team’s ability to influence, provide supporting documentation to the Director of Sustainability and demonstrating how the project will otherwise meet the LEED certification requirement. |  | Update LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard Within 90 days of 100% design, complete design team LEED documentation in LEED online. Perform a QC review and notify the UW LEED Admin that documentation is ready for internal review. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points is exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  | Update LEED scorecard Within 90 days of substantial completion, complete design team and contractor LEED documentation in LEED Online. Perform a QC review and notify the UW LEED Admin that documentation is ready for internal review. UW LEED Admin to coordinate commissioning documentation with CxP and complete LEED certification process. Target is to earn LEED certification within 9 months of substantial completion. |  | Documented with LEED credit documentation. Compiled by UW LEED Admin.
| Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 1 projects. | Y | List Fitwel v3 credits under evaluation. |  | Confirm Fitwel v3 credit planned to pilot. |  | N/A |  | N/A |  | Indicate the Fitwel credit pursued. |  | N/A |  | Fitwel v3 credit documentation.
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include new or alterations to existing building envelope? |  | Identify the applicable UW Bird-Friendly Design Guidelines. |  | Confirm the UW Bird-Friendly Design Guidelines planned for the project. |  | N/A |  | N/A |  | Confirm the UW Bird-Friendly Design Guidelines included in the project. |  | N/A |  | No additional documentation required.
HEALTH AND WELL-BEING | New construction projects must include showers and changing facilities. Major renovation projects evaluate options to provide showers and changing facilities. Applicable to all Tier 1 projects. | Y | Describe opportunities for new or improved showers and changing facilities for staff or to include other features and materials that support health and well-being. |  | Confirm plans for new or improved showers and changing facilities or other health and well-being strategies. |  | N/A |  | N/A |  | Confirm new or improved showers and changing facilities or other health and well-being strategies included in the project. |  | N/A |  | No additional documentation required.
EQUITY | Lactation facilities - New buildings and major renovation projects should include lactation facilities that support infant feeding, nursing, and pumping of breast milk for building occupants. Applicable to all Tier 1 projects. | Y | Describe opportunities for new or improved lactation facilities for staff or to include other features that support equity. |  | Confirm plans for new or improved lactation facilities or other equity strategies. |  | N/A |  | N/A |  | Confirm newor improved lactation facilities or other equity strategies included in the project. |  | N/A |  | No additional documentation required.
| UW Gender-Neutral Restroom policy - does the building include new or renovated restrooms ? |  | Follow UW Gender Neutral Restroom policy. Track any variances with other project variances. |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | No additional documentation required.
|  |  | Project Development Result |  | Project Definition Milestone Result |  | Early Design Milestone Result |  | Mid Design Milestone Result |  | Mid Design Milestone Result |  | Close out Result
|  |  | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | On track | All Yes (green) | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Yes (green) and In Progress or Concerns (yellow) | Still in development | Any No (red) | Does not comply
|  |  | Any No (red) | Off track | Any No (red) | Off track | Any No (red) | Off track | Any No (red) | Off track | Any No (red) | Off track