## Instructions
UW Green Building Standard Workbook
| Purpose: for tracking and reporting on GBS compliance | [5 empty] | EP status
The tabs in this workbook are color coded to match the steps in the process below.
2/14 - Have reviewed and edited top two categories in all Tiers
1. How to use this workbook: | [6 empty] | 2/19 - Step 3 - Tiers 4 and 3 are done (for now). Tier 2b in progress.
| Project Formation |  |  |  | Execution
| Project Initiation |  |  | Project Development
2. How to fill out the worksheets:
Cells filled with grey are not applicable and do not need to be filled out.
Cells requiring a yes or no answer have drop downs with "Y" and "N" choices.
Guidance for completing each open cell is in grey.
Provide responses in cells that are white
Based on the response provided in open cells, indicate status in the adjacent cells that have a drop down and formatting like this:
| On track |  | Complies
| Still in development | or this: | Does not comply
Off track
If the project receives a variance for a GBS requirement, note this in the report and do not select a status for that requirement.
Direct any questions about this workbook process and/or specific project eligibility to UW Sustainability at greenbuildings@uw.edu.
3. Example of filled rows
GBS Workbook Version Last Updated: 4/17/26
CAP
Start here - Make a copy of this workbook file and add it to project files
Answer the 'yes-no' questions in the Step 1 worksheet to confirm the GBS is applicable to the project.
Applicable?
Answer the 'yes-no' questions in the Step 2 worksheet to confirm the GBS Tier applicable to the project.
Go to the Step 3 worksheet for the appropriate Tier and determine the applicable requirements.
Continue to use the Step 3 worksheet for tracking and reporting on GBS compliance for the remainder of the project.
Report on GBS compliance issues at project milestones listed in the workbook
You may delete Step 3 and Step 4 worksheets for tiers not applicable to the project. To delete worksheets, under the Review tab in the top ribbon, turn off "Protect sheet" (there is no password); right-click on the worksheet tab and select "delete"
Yes
Requirements?
If not applicable, save this workbook in the project file as a record of the result.
No
If there are no applicable requirements, save this workbook to the project file as a record of the result.
No
Yes
Complete Step 4 - Project Summary and
submit a copy of the final workbook and any required documentation to UW Sustainability at greenbuildings@uw.edu

## Step 1 - Confirm Applicability
PHASE: Project Formation
SUBPHASE: Project Initiation
GBS Applicability
| Question | Y/N | If Yes | If No | Notes
a | Is this a capital project (see Notes)? |  | Continue to question b. | GBS is N/A, stop here. | Exclude maintenance projects, "planning" projects where capital dollars are being used for planning (e.g. a MIMP) or studies, commissioning, "patch and paint," and equipment used by staff to do the job (e.g. safety radios).
b | Is the budget $1,000,000 or greater? |  | Continue to question c. | GBS is N/A, stop here. | This is the Total Project Budget.
c | Is it in Washington State? |  | Continue to question d. | GBS is N/A, stop here.
d | Is it for a property that is owned and operated by the UW? |  | Continue to question e. | GBS not currently applicable, stop here. | These project will have GBS requirements when Phase 2 is launched.
e | Did/will the project complete project formation after June 30, 2024? |  | GBS v2 is applicable. Proceed to step 2. | GBS v2 is not required. GBS v1 may apply. | Projects required to do GBS v1 must work with UW Sustainability to agree on GBS v2 elements to incorporate into the project wherever possible.

## Step 2 - Determine Tier
PHASE: Project Formation
SUBPHASE: Project Initiation
Tier Identification
|  | Y/N | If Yes | If No | Notes
a | Is this project new construction or major renovation of a whole building or stand alone addition? |  | Project is Tier 1, proceed to question 'g' and enter Tier 1 as the answer. | Continue to question 'b'.
b | Is the project upgrading or adding new mechanical, electrical, or plumbing equipment or systems that consume or influence consumption of energy or water (see Notes)? |  | Continue to question 'c'. | Continue to question 'f'. | e.g. applies to fume hoods and elevators, but not to switch gear, applies to elevator modernization, but not door upgrades with LV controls. Applies to distribution or controls projects where options directly influence energy consumption. Exclude low voltage technology and fire safety systems.
c | Is there additional project scope on the building structure or finishes beyond direct impacts of the system upgrade? |  | Project may be Tier 2, continue to question 'd' to distinguish between 2a and 2b. | Project is Tier 3, proceed to question 'g' and enter Tier 3 as the answer.
d | Is the total project budget greater than $20M and is the project eligible for LEED v4 Commercial Interiors certification? |  | Project is Tier 2a, proceed to question 'g' and enter Tier 2a as the answer. | Project may be Tier 2b continue to question 'e'.
e | Is the project receiving State funding that requires LEED Silver certification? |  | Project is Tier 2b with a State LEED Silver requirement, proceed to question 'g' and enter Tier 2b as the answer. | Project may be Tier 2b continue to question 'f'.
f | Is the project comprised of any materials where the Carbon Leadership Forum has established embodied carbon baselines in its most current baseline report (see Notes)? |  | Projects that said "Y" to question 'b', are Tier 2b, proceed to question 'g' and enter Tier 2b as the answer. Projects that said "N" to question 'b' are Tier 4, proceed to question 'g' and enter Tier 4 as the answer. | No applicable GBS requirements, stop here. | - Refer to definitions of materials in CLF baseline report - Where there are no applicable GBS requirements, the GBS is not applicable to the project. -CLF reports at this link: https://carbonleadershipforum.org/resource-library/
g | What Tier is the project? Answering the questions above will help you determine this; also see 'Definitions' below. |  |  |  | - Use tab Step 3 to report GBS progress throughout project - Use tab Step 4 to summarize GBS compliance at the end of the project - You may delete any Step 3 and Step 4 tabs that do not pertain to your Tier
Direct any questions about specific project eligibility to UW Sustainability at greenbuildings@uw.edu.
Tier Definitions
Description
Tier 1 | New construction and major renovation | New ground up construction, major renovations of whole buildings and stand-alone additions.
Tier 2a | Partial building renovations | Projects that include multiple system upgrades or renovations (HVAC, plumbing, lighting, finishes) and that have distinct, contiguous space eligible for LEED v4 certification.
Tier 2b | Interiors projects | Projects that include multiple system upgrades or renovations (HVAC, plumbing, lighting, finishes). Scope may be distributed throughout a building, not eligible for LEED v4 certification.
Tier 3 | System upgrades | Projects that are upgrading or adding new mechanical, electrical, and plumbing equipment or systems that will consume or influence the University's consumption of energy or water and that do not include additional scope.
Tier 4 | Non-energy projects | Non-energy projects involving materials but limited or no systems.

## Step 3 - Tier 4 Track & Report
Tier 4 GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project using the provided guidance. Add project specific responses in the Response column. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that subphase. Contact UW Sustainability if there are Concerns or anything is "Off Track." | PHASE: Project Formation |  |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  |  | SUBPHASE: Early Design Milestone |  |  | SUBPHASE: Close out
Topic | Requirement | Applicable? | Initial Project Approach | Response | On track? | Confirm Project Approach | Response | On track? | Report Project Results | Response | Completed? | Required documentation
PROCESS/INSTRUCTIONS | Follow UW GBS Process per Process Map and Green Building Standard - applicable to all Tier 4 projects. | Y | INSTRUCTIONS: - Complete these columns at the end of project formation. |  |  | INSTRUCTIONS: - Complete these columns at an early-design milestone. |  |  | INSTRUCTIONS: - Complete these columns at the end of the project. - Submit final workbook and the required documentation to greenbuildings@uw.edu at the end of the project.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments - applicable to all Tier 4 projects. | Y | Track any variances from UW standards separately. |  |  | N/A |  |  | N/A |  |  | N/A
EMBODIED CARBON | Product embodied carbon limits - For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit - applicable to all Tier 4 projects. | Y | Indicate the applicable CLF Material Baselines report year. List likely applicable materials in the project. |  |  | List confirmed applicable materials and the kgCO2e per declared unit limit. |  |  | List applicable materials used on the project and the kgCO2e per declared unit . |  |  | Compiled EPDs.
HEALTH AND WELL-BEING | Are there opportunities to include features and materials that support health and well-being in this project? |  | Indicate any opportunities for the project that support health and well-being. |  |  | Indicate strategies planned for the project that support health and well-being. |  |  | Confirm strategies included in the project that support health and wellbeing. |  |  | No additional documentation required.
EQUITY | Are there opportunities to include features and materials that support equity in this project? |  | Indicate any opportunities for the project that support equity. |  |  | Indicate strategies planned for the project that support equity. |  |  | Confirm strategies included in the project that support equity. |  |  | No additional documentation required.
|  |  |  | Project Development Result |  |  | Early Design Milestone Result |  |  | Close out Result
|  |  |  | All Yes (green) | On track |  | All Yes (green) | On track |  | All Yes (green) | Complies
|  |  |  | Yes (green) and In Progress or Concerns (yellow) | Still in development |  | Yes (green) and In Progress or Concerns (yellow) | Still in development |  | Any No (red) | Does not comply
|  |  |  | Any No (red) | Off track |  | Any No (red) | Off track

## Step 3 - Tier 3 Track & Report
Tier 3 GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project using the provided guidance. Add project specific responses in the Response column. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that subphase. Contact UW Sustainability if there are Concerns or anything is "Off Track." | PHASE: Project Formation |  |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  |  | SUBPHASE: Early Design Milestone |  |  | SUBPHASE: Close out
Topic | Requirement | Applicable? | Initial Project Approach | Response | On track? | Confirm Project Approach | Response | On track? | Report Project Results | Response | Complete? | Required documentation
PROCESS/INSTRUCTIONS | Follow UW GBS Process per Process Map and Green Building Standard - applicable to all Tier 3 projects. | Y | INSTRUCTIONS: - Complete these columns at the end of project formation. |  |  | INSTRUCTIONS: - Complete these columns at an early-design milestone. |  |  | INSTRUCTIONS: - Complete these columns at the end of the project. - Complete Step 4 - Project Summary worksheet tab in this workbook. - Submit final workbook and the required documentation to greenbuildings@uw.edu at the end of the project.
LIFE CYCLE COST ANALYSIS | UW LCCA requirements - does project meet definition of major or minor project in the UW LCCA Requirements? |  | Indicate what options or systems the LCCA will evaluate. |  |  | Summarize results of LCCA. |  |  | N/A |  |  | LCCA Report.
| State ELCCA - Does the state funding require ELCCA on this project? |  | N/A |  |  | 1) Confirm State required ELCCA workplan submited to the state. 2) Complete EELCCA by mid-design milestone and submit to the state. |  |  | N/A |  |  | ELCCA Report.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments - applicable to all Tier 3 projects. | Y | Track any variances from UW standards separately |  |  | N/A |  |  | N/A |  |  | No documentation required.
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate plans for connecting to district energy. |  |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  |  | Confirm use(s) of fossil fuels on the project and estimated annual fossil fuel use. |  |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA may be necessary to justify keeping or adding fossil fuels. |  |  | Confirm project is on track for connecting to district energy. |  |  | Indicate here if project connected to district energy. |  |  | No additional documentation required.
| Energy conservation measures - Are there opportunities to use different or more efficient systems or equipment or otherwise save energy on the project (ECMs)? |  | Summarize opportunities for energy conservation. |  |  | Indicate energy conservation measures planning to include in the project and estimated energy savings. |  |  | Confirm energy conservation measures included and estimated energy savings. |  |  | Back up calculations for estimated energy savings through energy conservation.
| Energy Use Intensity (EUI) Targets (EUIt): Does the project include substantial modification to the mechanical and electrical systems, meeting the definition for minor renovation in the UW LCCA requirements? |  | Calculate EUIt by activity for the spaces within the project scope per CBPS. |  |  | Provide the project's estimated EUI. |  |  | Provide the project's final EUI. |  |  | No additional documentation required.
| Is the project located in Seattle and not connecting to the district energy system? |  | Calculate GHGi target by activity for the spaces within the project scope per BEPS. |  |  | Provide the project's estimated GHGi. |  |  | Provide the project's final GHGi. |  |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS or other University standards? |  | Identify water consuming fixtures, appliances, or equipment with their efficiency requirement. |  |  | Confirm water consuming fixtures, appliances, and equipment planned for the project meets or exceeds efficiency standards. |  |  | List water consuming fixtures, appliances, and equipment used in the project and their efficiency. Confirm they all meet or exceed standard. |  |  | No additional documentation required.
| Supporting low-flow fixtures - is the project upgrading plumbing and/or replacing drainlines? |  | Indicate if there are applicable opportunities to address barriers to low-flow fixture installation or performance. |  |  | Describe any improvements to support low flow fixtures planned for the project. |  |  | Indicate if improvements to support low flow fixtures included in the project. |  |  | No additional documentation required.
EMBODIED CARBON | Embodied carbon reporting requirements are not applicable to Tier 3 projects. Project teams are encouraged to investigate the latest information available on embodied carbon in systems and equipment and consider how to reduce embodied carbon. Answer yes, "Y", if opportunities to reduce embodied carbon are available. |  | Indicate any opportunities in the project that reduce embodied carbon. |  |  | Indicate strategies planned for in the project that reduce embodied carbon and indicate the estimated reduction. |  |  | Indicate here strategies included in the project that reduced embodied carbon and indicate here the estimated reduction. |  |  | No additional documentation required.
HEALTH AND WELL-BEING | Are there opportunities to include features and materials that support health and well-being in this project? |  | Indicate any opportunities for the project that support health and well-being. |  |  | Indicate strategies planned for the project that support health and well-being. |  |  | Confirm strategies included in the project that support health and wellbeing. |  |  | No additional documentation required.
EQUITY | Are there opportunities to include features and materials that support equity in this project? |  | Indicate any opportunities for the project that support equity. |  |  | Indicate strategies planned for the project that support equity. |  |  | Confirm strategies included in the project that support equity. |  |  | No additional documentation required.
|  |  | Project Development Result |  |  | Early Design Milestone Result |  |  | Close out Result
|  |  | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Any No (red) |  | Does not comply
|  |  | Any No (red) |  | Off track | Any No (red) |  | Off track

## Step 3 Tier 2b Track and Report
Tier 2b GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project using the provided guidance. Add project specific responses in the Response column. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that subphase. Contact UW Sustainability if there are Concerns or anything is "Off Track." | PHASE: Project Formation |  |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  |  | SUBPHASE: Early Design Milestone |  |  | SUBPHASE: Close out
Topic | Requirement | Applicable? | Initial Project Approach | Response | On track? | Confirm Project Approach | Response | On track? | Report Project Results | Response | Complete? | Required documentation
PROCESS/INSTRUCTIONS | Follow UW GBS Process per Process Map and Green Building Standard - applicable to all Tier 2b projects. | Y | INSTRUCTIONS: - Complete these columns at the end of project formation. |  |  | INSTRUCTIONS: - Complete these columns at an early-design milestone. |  |  | INSTRUCTIONS: - Within 90 days of substantial completion complete these columns. - Complete Step 4 - Project Summary worksheet tab in this workbook. - Submit final workbook and required documentation to greenbuildings@uw.edu within 90 days of substantial completion.
LIFE CYCLE COST ANALYSIS | UW LCCA requirements - does project meet definition of major or minor project in the UW LCCA Requirements? |  | Indicate what options or systems the LCCA will evaluate. |  |  | Summarize results of LCCA. |  |  | N/A |  |  | LCCA Report
| State ELCCA - Does the state funding require ELCCA on this project? |  | N/A |  |  | 1) Confirm State required ELCCA workplan submited to the state. 2) Complete ELCCA by mid-design milestone and submit to the state. |  |  | N/A |  |  | ELCCA Report.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 2b projects. | Y | Track any variances from UW standards separately |  |  | Track any variances related to the GBS in variance log |  |  | Confirm all related variances closed out
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA may be necessary to justify keeping or adding fossil fuels. |  |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  |  | Confirm use(s) of fossil fuels on the project and estimated annual fossil fuel use. |  |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate plans for connecting to district energy. |  |  | Confirm project is on track for connecting to district energy. |  |  | Indicate here if project connected to district energy. |  |  | No additional documentation required.
| Energy conservation measures - Are there opportunities to use different or more efficient systems or equipment or otherwise save energy on the project (ECMs)? |  | Summarize opportunities for energy conservation. |  |  | Indicate energy conservation measures planning to include in the project and estimated energy savings. |  |  | Confirm energy conservation measures included and estimated energy savings. |  |  | Back up calculations for estimated energy savings through energy conservation.
| Energy Use Intensity (EUI) Targets (EUIt): Does the project include substantial modification to the mechanical and electrical systems, meeting the definition for minor renovation in the UW LCCA requirements? |  | Calculate EUIt by activity for the spaces within the project scope per CBPS and list results here. |  |  | Confirm the applicable target Provide the estimated EUI for the spaces within the project scope. |  |  | Provide the final EUI for the spaces within the project scope. |  |  | No additional documentation required.
| Is the project located in Seattle and not connecting to the district energy system? |  | Calculate GHGi target by activity for the spaces within the project scope per BEPS and list results here. |  |  | Confirm the applicable target Provide the estimated GHGi for the spaces within the project scope. |  |  | Provide the final GHGi for the spaces within the project scope. |  |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS or other University standards? |  | List likely water consuming fixtures, appliances, or equipment. |  |  | List the water consuming fixtures, appliances, and equipment planned for the project and their efficiency standards. |  |  | N/A |  |  | No additional documentation required.
| Water efficiency target - Achieve the required % reduction from LEED ID+C v4 baseline unless existing plumbing will not support lower flow. |  | Indicate required percent reduction here. |  |  | Update water savings or confirm project on-track |  |  | Enter the water savings from final fixtures, appliances, and equipment. |  |  | Indoor Water Use Reduction calculator.
EMBODIED CARBON | Product embodied carbon limits - For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. Applicable to all Tier 2b projects. | Y | Indicate the applicable CLF Material Baselines report year. List likely applicable materials in the project. |  |  | List confirmed applicable materials and the kgCO2e per declared unit limit. |  |  | List applicable materials used on the project and the kgCO2e per declared unit . |  |  | Compiled EPDs.
RATING SYSTEM | Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 2b projects. | Y | List Fitwel v3 credits under evaluation. |  |  | Confirm Fitwel v3 credit planned to pilot. |  |  | Indicate the Fitwel credit pursued. List any lessons learned from piloting credit. |  |  | Fitwel v3 credit documentation.
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include alterations to the building envelope? |  | Identify the applicable UW Bird-Friendly Design Guidelines. |  |  | Confirm the UW Bird-Friendly Design Guidelines planned for the project. |  |  | Confirm the UW Bird-Friendly Design Guidelines included in the project. |  |  | No additional documentation required.
HEALTH AND WELL-BEING | Showers and changing facilities - Is there an opportunity for this project to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being in this project? |  | Describe opportunities to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being. |  |  | Confirm plans for added or improved showers and changing facilities or other health and well-being strategies. |  |  | Confirm added or improved showers and changing facilities or other health and well-being strategies included in the project. |  |  | No additional documentation required.
| Projects are encouraged to create a Healthy Materials Plan that identifies material ingredients to be avoided as much as possible on the project and how they will be specififed and tracked. This is applicable to all Tier 1 projects, but optional to pursue. | Y | Describe opportunities for using healthier materials or reducing chemicals of concern for user groups of the project. |  |  | Define healthy materials goals for project. Confirm if a Healthy Materials Plan will be created for project. If so, confirm how healthy material options will be specified and tracked during design and construction. |  |  | Confirm how Healthy Materials Plan was tracked during construction (if applicable). |  |  | Healthy Materials Plan (if applicable).
EQUITY | Lactation facilities - Is there an opportunity for this project to add or improve lactation facilities for staff or to include other features that support equity on this project. |  | Describe opportunities to add or improve lactation facilities for staff or to include other features that support equity. |  |  | Confirm plans for added or improved lactation facilities or other equity strategies. |  |  | Confirm added or improved lactation facilities or other equity strategies included in the project. |  |  | No additional documentation required.
| UW Gender Inclusive Restroom Design Guidance - are restrooms being added or improved as part of this project? |  | Follow UW Gender Inclusive Restroom Design Guidance in FDS. Track any variances with other project variances. |  |  | N/A |  |  | N/A |  |  | No additional documentation required.
|  |  | Project Development Result |  |  | Early Design Milestone Result |  |  | Close out Result
|  |  | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Any No (red) |  | Does not comply
|  |  | Any No (red) |  | Off track | Any No (red) |  | Off track

## Step 3 Tier 2a Track and Report
Tier 2a GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project using the provided guidance. Add project specific responses in the Response column. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that subphase. Contact UW Sustainability if there are Concerns or anything is "Off Track." | PHASE: Project Formation |  |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  |  | SUBPHASE: Project Definition |  |  | SUBPHASE: Early Design Milestone |  |  | SUBPHASE: Post 100% Design Milestone |  |  | SUBPHASE: Close out
Topic | Requirement | Applicable? | Initial Project Approach | Response | On track? | Confirm Project Approach | Response | On track? | Update on Project Approach | Response | On track? | Update on Project Approach | Response | On track? | Report Project Results | Response | Complete? | Required documentation
PROCESS/INSTRUCTIONS | Follow UW GBS Process per Process Map and Green Building Standard - applicable to all Tier 2a projects. | Y | INSTRUCTIONS: - Complete these columns at the end of project formation. |  |  | INSTRUCTIONS: - Complete these columns at the end of project definition. |  |  | INSTRUCTIONS: - Complete these columns at an early-design milestone. |  |  | INSTRUCTIONS: - Within 90 days of 100% design complete these columns. |  |  | INSTRUCTIONS: - Within 90 days of substantial completion complete these columns. - Complete Step 4 - Project Summary worksheet tab in this workbook. - Submit final workbook and required documentation to greenbuildings@uw.edu within 90 days of substantial completion.
LIFE CYCLE COST ANALYSIS | UW LCCA requirements - does project meet definition of major or minor project in the UW LCCA Requirements? |  | Indicate what options or systems the LCCA will evaluate. |  |  | Confirm LCCA submitted to CEUO. |  |  | N/A |  |  | N/A |  |  | N/A |  |  | LCCA Report.
| State ELCCA - Does the state funding require ELCCA on this project? |  | N/A |  |  | N/A |  |  | Confirm State required ELCCA workplan submited to the state. |  |  | Confirm ELCCA complete and submitted to the state. |  |  | N/A |  |  | ELCCA Report.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments - applicable to all Tier 2a projects. | Y | Track any variances from UW standards separately |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA may be necessary to justify keeping or adding fossil fuels. |  |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  |  | N/A |  |  | Confirm use(s) of fossil fuels on the project and estimated annual fossil fuel use. |  |  | N/A |  |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate plans for connecting to district energy. |  |  | Confirm project is on track for connecting to district energy. |  |  | N/A |  |  | Confirm project is on track for connecting to district energy. |  |  | Indicate here if project connected to district energy. |  |  | No additional documentation required.
| Energy conservation measures - Are there opportunities to use different or more efficient systems or equipment or otherwise save energy on the project (ECMs)? |  | Summarize opportunities for energy conservation. |  |  | N/A |  |  | Indicate energy conservation measures planned for inclusion in the project. |  |  | Confirm energy conservation measures included in the project.Document energy savings in LEED energy model as applicable. |  |  | N/A |  |  | No additional documentation required.
| Energy Use Intensity (EUI) Targets (EUIt): Does the project include substantial modification to the mechanical and electrical systems, meeting the definition for minor renovation in the UW LCCA requirements? |  | Calculate EUIt by activity for the spaces within the project scope per CBPS and indicate the results here. |  |  | Confirm the applicable target with any changes in gross floor area of use of spaces. |  |  | Provide the estimated EUI for the spaces within the project scope showing compliance with the target. |  |  | Provide the final EUI for the spaces within the project scope. |  |  | N/A |  |  | No additional documentation required.
| Is the project located in Seattle and not connecting to the district energy system? |  | Calculate GHGi target by activity for the spaces within the project scope per BEPS and indicate the results here. |  |  | Confirm the applicable target with any changes in gross floor area of use of spaces. |  |  | Provide the estimated GHGi for the spaces within the project scope showing compliance with the target. |  |  | Provide the final GHGi for the spaces within the project scope. |  |  | N/A |  |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS? |  | List likely water consuming fixtures, appliances, or equipment. |  |  | List the water consuming fixtures, appliances, and equipment planned for the project and their efficiency standards. |  |  | List the water consuming fixtures, appliances, and equipment planned for the project and their efficiency standards. |  |  | N/A |  |  | N/A |  |  | No additional documentation required.
| Water efficiency target - Achieve the required % reduction from LEED ID+C v4 baseline unless existing plumbing will not support lower flow. |  | Indicate required percent reduction here. |  |  | Perform preliminary water savings calculations to plan which fixtures and which flow rates to include in the project. Enter estimated water savings and confirm if on-track. |  |  | Update water savings or confirm project on-track |  |  | Enter the water savings from final fixtures, appliances, and equipment. |  |  | N/A |  |  | Indoor Water Use Reduction calculator.
EMBODIED CARBON | Product embodied carbon limits - For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. Applicable to all Tier 2a projects. | Y | Indicate the applicable CLF Material Baselines report year. List likely applicable materials in the project. |  |  | Update list of likely applicable materials in the project and the kgCO2e per declared unit limit. |  |  | Confirm low-GWP materials requirements and the kgCO2e per declared unit limit is in the specifications. |  |  | N/A |  |  | List applicable materials used on the project and the actual kgCO2e per declared unit . |  |  | Compiled EPDs and EPD summary report from EC3.
| At the end of the project, report as-built embodied carbon of actual new construction materials using the EC3 tool and following the LEED pilot credit for Procurement of Low-Carbon Construction Materials (MRpc132). Applicable to all Tier 2a projects. | Y | N/A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | Complete calculation following the LEED pilot credit. List total embodied carbon footprint baseline and actual here. |  |  | EC3 report showing baseline and actual embodied carbon footprint of new materials used on the project. If the project pursues Procurement of Low-Carbon Construction Materials (MPpc132) LEED credit documentation suffices for documentation, include A4 in EC3.
RATING SYSTEM | Target LEED CI Gold and earn required credits in the UW LEED CI scorecard, including one innovation or pilot credit from the preferred list. Applicable to all Tier 2a projects. | Y | Provide LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  |  | Provide updated LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points Describe any exceptions to individual required LEED credits that may be unachievable due to project constraints outside of the project team's ability to influence. If applicable, save supporting documentation to provide with GBS documentation at closeout. |  |  | Provide updated LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  |  | Provide updated LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points is exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  |  | Indicate final LEED scoring and certification level here. |  |  | Final LEED Scorecard. Full LEED Documentation into Google Drive per UW Closeout Instructions. If any UW required credits not pursued, provide backup documentation if applicable
| Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 2a projects. | Y | List Fitwel v3 credits under evaluation. |  |  | Confirm Fitwel v3 credit planned to pilot. |  |  | N/A |  |  | Indicate the Fitwel credit pursued. List any lessons learned from piloting credit. |  |  | N/A |  |  | Fitwel v3 credit documentation.
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include alterations to the building envelope? |  | Identify the applicable UW Bird-Friendly Design Guidelines. |  |  | Confirm the UW Bird-Friendly Design Guidelines planned for the project. |  |  | N/A |  |  | Confirm the UW Bird-Friendly Design Guidelines included in the project. |  |  | N/A |  |  | No additional documentation required.
HEALTH AND WELL-BEING | Showers and changing facilities - Is there an opportunity for this project to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being in this project? |  | Describe opportunities to add or improve showers and changing facilities for staff or to include other features and materials that support health and well-being. |  |  | Confirm plans for added or improved showers and changing facilities or other health and well-being strategies. |  |  | N/A |  |  | Confirm added or improved showers and changing facilities or other health and well-being strategies included in the project. |  |  | N/A |  |  | No additional documentation required.
| Projects are encouraged to create a Healthy Materials Plan that identifies material ingredients to be avoided as much as possible on the project and how they will be specififed and tracked. This is applicable to all Tier 1 projects, but optional to pursue. | Y | Describe opportunities for using healthier materials or reducing chemicals of concern for user groups of the project. |  |  | Define healthy materials goals for project. |  |  | Confirm if a Healthy Materials Plan will be created for project. If so, confirm how healthy material options will be specified and tracked during design and construction. |  |  | N/A |  |  | Confirm how Healthy Materials Plan was tracked during construction (if applicable). |  |  | Healthy Materials Plan (if applicable).
EQUITY | Lactation facilities - Is there an opportunity for this project to add or improve lactation facilities for staff or to include other features that support equity on this project. |  | Describe opportunities to add or improve lactation facilities for staff or to include other features that support equity. |  |  | Confirm plans for added or improved lactation facilities or other equity strategies. |  |  | N/A |  |  | Confirm added or improved lactation facilities or other equity strategies included in the project. |  |  | N/A |  |  | No additional documentation required.
| UW Gender Inclusive Restroom Design Guidelines - are restrooms being added or improved as part of this project? |  | Follow UW Gender Inclusive Restroom Design Guidelines. Track any variances with other project variances. |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No additional documentation required.
|  |  | Project Development Result |  |  | Project Definition Milestone Result |  |  | Early Design Milestone Result |  |  | Post Design Milestone Result |  |  | Close out Result
|  |  | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Any No (red) |  | Does not comply
|  |  | Any No (red) |  | Off track | Any No (red) |  | Off track | Any No (red) |  | Off track | Any No (red) |  | Off track

## Step 3 Tier 1 Track and Report
Tier 1 GBS Tracking and Reporting
Instructions: Complete each column at the end of the corresponding Project Subphase of the project using the provided guidance. Add project specific responses in the Response column. Finish by selecting the appropriate 'Result' at the bottom of the "On Track" column in that subphase. Contact UW Sustainability if there are Concerns or anything is "Off Track." | PHASE: Project Formation |  |  |  |  | PHASE: Project Execution
| SUBPHASE: Project Initiation |  | SUBPHASE: Project Development |  |  | SUBPHASE: Project Definition |  |  | SUBPHASE: Early Design Milestone |  |  | SUBPHASE: Post 100% Design Milestone |  |  | SUBPHASE: Close out
Topic | Requirement | Applicable? | Initial Project Approach | Response | On track? | Confirm Project Approach | Response | On track? | Update on Project Approach | Response | On track? | Update on Project Approach | Response | On track? | Report Project Results | Response | Complete? | Required documentation
PROCESS/INSTRUCTIONS | Follow UW GBS Process per Process Map and Green Building Standard - applicable to all Tier 1 projects. | Y | INSTRUCTIONS: - Complete these columns at the end of project formation. |  |  | INSTRUCTIONS: - Complete these columns at the end of project definition. |  |  | INSTRUCTIONS: - Complete these columns at an early-design milestone. |  |  | INSTRUCTIONS: - Within 90 days of 100% design complete these columns. |  |  | INSTRUCTIONS: - Within 90 days of substantial completion complete these columns. - Complete Step 4 - Project Summary worksheet tab in this workbook. - Submit final workbook and required documentation to greenbuildings@uw.edu within 90 days of substantial completion.
LIFE CYCLE COST ANALYSIS | Apply UW LCCA requirements |  | Indicate what options or systems the LCCA will evaluate. |  |  | Confirm LCCA submitted to CEUO. |  |  | N/A |  |  | N/A |  |  | N/A |  |  | LCCA Report.
| State ELCCA |  | N/A |  |  | N/A |  |  | Confirm State required ELCCA workplan submited to the state. |  |  | Confirm ELCCA complete and submitted to the state. |  |  | N/A |  |  | ELCCA Report.
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 1 projects. | Y | Track any variances from UW standards separately |  |  | Track any variances related to the GBS in variance log |  |  | Track any variances related to the GBS in variance log | [5 empty] | Confirm all related variances closed out
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? |  | Indicate any existing or new planned fossil fuel equipment or systems in the building that may be necessary for the project. Note that LCCA may be necessary to justify keeping or adding fossil fuels. |  |  | Indicate resolution on use of fossil fuels on the project and note estimated annual fossil fuel use. |  |  | N/A |  |  | Confirm use(s) of fossil fuels on the project and enter estimated annual fossil fuel use in this cell. |  |  | N/A |  |  | No additional documentation required.
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. |  | Indicate plans for connecting to district energy. |  |  | Confirm project is on track for connecting to district energy. |  |  | N/A |  |  | Confirm project is on track for connecting to district energy. |  |  | Indicate here if project connected to district energy. |  |  | No additional documentation required.
| Energy Use Intensity (EUI) targets (EUIt): Design the building to perform better than the Washington State Clean Buildings Performance Standard (CBPS) EUIt for the building type and activities. Applicable to all Tier 1 projects. | Y | Calculate EUIt for the building per CBPS and indicate the results here. |  |  | Confirm the applicable target with any changes in gross floor area. |  |  | Provide the estimated EUI for the building showing compliance with the target. |  |  | Provide the final EUI for the building. |  |  | N/A |  |  | No additional documentation required.
| Is the project located in Seattle and not connecting to the district energy system? |  | Calculate GHGi target for the building per BEPS and indicate the results here. |  |  | Confirm the applicable target with any changes in gross floor area. |  |  | Provide the estimated GHGi for the building showing compliance with the target. |  |  | Provide the final GHGi for the building. |  |  | N/A |  |  | No additional documentation required.
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS? |  | Identify likely water consuming fixtures, appliances, or equipment. |  |  | List the water consuming fixtures, appliances, and equipment planned for the project and their efficiency standards. |  |  | List the water consuming fixtures, appliances, and equipment planned for the project and their efficiency standards. |  |  | N/A |  |  | N/A |  |  | No additional documentation required.
| Water efficiency target - Achieve the required % reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. |  | Indicate required percent reduction here. |  |  | Perform preliminary water savings calculations to plan which fixtures and which flow rates to include in the project. Indicate estimated percent savings and confirm if on-track. |  |  | Update water savings or confirm project on-track |  |  | Enter % water savings from final fixtures, appliances, and equipment. |  |  | N/A |  |  | Indoor Water Use Reduction calculator.
EMBODIED CARBON | Product embodied carbon limits: For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. Applicable to all Tier 1 projects. | Y | Indicate the applicable CLF Material Baselines report year. List likely applicable materials in the project. |  |  | Update list of likely applicable materials in the project and the kgCO2e per declared unit limit. |  |  | Confirm low-GWP materials requirements and the kgCO2e per declared unit limit is in the specifications. |  |  | N/A |  |  | List applicable materials used on the project and the actual kgCO2e per declared unit . |  |  | Compiled EPDs and EPD summary report from EC3.
| Identify strategies to reduce the embodied carbon of the project and perform calculations to set a project-specific as-designed total embodied carbon target. Do not exceed the total embodied carbon limit of 500 kgCO2e/m2. Applicable to all Tier 1 projects. | Y | N/A |  |  | Determine the expected total project as-designed embodied carbon using a life cycle assessment(LCA) tool. Indicate the project-specific total as-designed embodied carbon target. Identify strategies to reduce the embodied carbon. |  |  | N/A |  |  | N/A |  |  | N/A |  |  | Output report from the LCA for the as-designed total embodied carbon. If project pursues LEED credit for Whole Building Life Cycle Assessment, LEED credit documentation compiled by UW LEED Admin suffices for documentation.
| Is this project a major renovation of an existing building? If so, estimate the embodied carbon impact of the materials required to build a new, similar building using EC3 and the LEED pilot credit (MRpc132) methodology. |  | N/A |  |  | N/A |  |  | N/A |  |  | Prepare the calculation of the embodied carbon impact of the materials required to build a new similar building using EC3 and the LEED pilot credit (MRpc132). Indicate total footprint here. |  |  | N/A |  |  | EC3 report with total embodied carbon footprint of a new, similar building.
| At the end of the project, report as-built embodied carbon of actual new construction materials using the EC3 tool and following the LEED pilot credit for Procurement of Low-Carbon Construction Materials (MRpc132). Applicable to all Tier 1 projects. | Y | N/A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | Complete calculation following the LEED pilot credit. List total embodied carbon footprint baseline and actual here. |  |  | EC3 report showing baseline and actual embodied carbon footprint of new materials used on the project. If the project pursues Procurement of Low-Carbon Construction Materials (MPpc132) LEED credit documentation suffices for documentation, include A4 in EC3.
RATING SYSTEM | Earn LEED v4 NC Gold certification including required credits in the UW LEED scorecard, and one innovation or pilot credit from the preferred list. Applicable to all Tier 1 projects. | Y | Provide LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  |  | Provide updated LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points Describe any exceptions to individual required LEED credits that may be unachievable due to project constraints outside of the project team's ability to influence. If applicable, save supporting documentation to provide with GBS documentation at closeout. |  |  | Provide updated LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  |  | Provide updated LEED scoring here. Indicate the On-Track Status as follows: Yes = total of "Yes" points exceeds 60 points In Progress = total of "Yes" and "Likely" points is exceeds 60 points Off track = total of "Yes" and "Likely" points is less than 60 points |  |  | Indicate final LEED scoring and certification level here. |  |  | Final LEED Scorecard. Full LEED Documentation into Google Drive per UW Closeout Instructions. If any UW required credits not pursued, provide backup documentation if applicable
| Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 1 projects. | Y | List Fitwel v3 credits under evaluation. |  |  | Confirm Fitwel v3 credit planned to pilot. |  |  | N/A |  |  | Indicate the Fitwel credit pursued. List any lessons learned from piloting credit. |  |  | N/A |  |  | Fitwel v3 credit documentation.
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include new or alterations to existing building envelope? |  | Identify the applicable UW Bird-Friendly Design Guidelines. |  |  | Confirm the UW Bird-Friendly Design Guidelines planned for the project. |  |  | N/A |  |  | Confirm the UW Bird-Friendly Design Guidelines included in the project. |  |  | N/A |  |  | No additional documentation required.
HEALTH AND WELL-BEING | New construction projects must include showers and changing facilities. Major renovation projects evaluate options to provide showers and changing facilities. Applicable to all Tier 1 projects. | Y | Describe opportunities for new or improved showers and changing facilities for staff or to include other features and materials that support health and well-being. |  |  | Confirm plans for new or improved showers and changing facilities or other health and well-being strategies. |  |  | N/A |  |  | Confirm added or improved showers and changing facilities or other health and well-being strategies included in the project. |  |  | N/A |  |  | No additional documentation required.
| Projects are encouraged to create a Healthy Materials Plan that identifies material ingredients to be avoided as much as possible on the project and how they will be specififed and tracked. This is applicable to all Tier 1 projects, but optional to pursue. | Y | Describe opportunities for using healthier materials or reducing chemicals of concern for user groups of the project. |  |  | Define healthy materials goals for project. |  |  | Confirm if a Healthy Materials Plan will be created for project. If so, confirm how healthy material options will be specified and tracked during design and construction. |  |  | N/A |  |  | Confirm how Healthy Materials Plan was tracked during construction (if applicable). |  |  | Healthy Materials Plan (if applicable).
EQUITY | Lactation facilities - New buildings and major renovation projects should include lactation facilities that support infant feeding, nursing, and pumping of breast milk for building occupants. Applicable to all Tier 1 projects. | Y | Describe opportunities for new or improved lactation facilities for staff or to include other features that support equity. |  |  | Confirm plans for new or improved lactation facilities or other equity strategies. |  |  | N/A |  |  | Confirm new or improved lactation facilities or other equity strategies included in the project. |  |  | N/A |  |  | No additional documentation required.
| UW Gender Inclusive Restroom Design Guidelines policy - does the building include new or renovated restrooms? |  | Follow UW Gender Inclusive Restroom Design Guidelines. Track any variances with other project variances. |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No additional documentation required.
|  |  | Project Development Result |  |  | Project Definition Milestone Result |  |  | Early Design Milestone Result |  |  | Post Design Milestone Result |  |  | Close out Result
|  |  | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | On track | All Yes (green) |  | Complies
|  |  | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Yes (green) and In Progress or Concerns (yellow) |  | Still in development | Any No (red) |  | Does not comply
|  |  | Any No (red) |  | Off track | Any No (red) |  | Off track | Any No (red) |  | Off track | Any No (red) |  | Off track

## Step 4 Summary Tier 4
0
PROCESS | Follow UW GBS Process - applicable to all Tier 1 projects.
LIFE CYCLE COST ANALYSIS | Apply UW LCCA requirements
State ELCCA
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 1 projects.
Step 4 |  | No additional reporting required for Tier 4.
- insulation
- metal panel cladding (not insulated)
- membrane roofing
- flat glass (not IGUs)
- gypsum board (lightweight, type X, and glass mat)
- resilient vinyl or rubber flooring
Review GBS for link/requirements for embodied carbon limits.

## Step 4 Summary Tier 3
Summary
Instructions: Enter answers as applicable, confirm the units. Shaded cells auto-fill |  | 0
|  |  | Enter Answer | Units
PROCESS | Follow UW GBS Process - applicable to all Tier 1 projects.
LIFE CYCLE COST ANALYSIS | Apply UW LCCA requirements
State ELCCA
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 1 projects.
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? | Use of fossil fuels on the project? Yes/No:
|  | Estimated annual fossil fuel use (if applicable): |  | BTUs
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. | Connected to District Energy System? Yes/No:
|  | EUI target: |  | kBTU/SF/year
|  | Final EUI: |  | kBTU/SF/year
|  | Estimated annual energy savings from ECMs: |  | BTUs
| Energy Use Intensity (EUI) targets (EUIt): Design the building to perform better than the Washington State Clean Buildings Performance Standard (CBPS) EUIt for the building type and activities. Projects located in Seattle and not connected to the Seattle campus district energy system must also plan for compliance with the City of Seattle Building Performance Standard (BEPS) Greenhouse Gas Intensity (GHGi) target. Applicable to all Tier 1 projects. | Final GHGi (if applicable): |  | kgCO2e/SF/year
- insulation
- metal panel cladding (not insulated)
- membrane roofing
- flat glass (not IGUs)
- gypsum board (lightweight, type X, and glass mat)
- resilient vinyl or rubber flooring
Review GBS for link/requirements for embodied carbon limits.

## Step 4 Summary Tier 2b
Summary
Instructions: Enter answers as applicable, confirm the units. Shaded cells auto-fill |  | 0
|  |  | Enter Answer | Units
PROCESS | Follow UW GBS Process - applicable to all Tier 1 projects.
LIFE CYCLE COST ANALYSIS | Apply UW LCCA requirements
State ELCCA
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 1 projects.
PROJECT INFO |  | Gross Floor Area (GFA): |  | SF
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? | Use of fossil fuels on the project? Yes/No:
|  | Estimated annual fossil fuel use (if applicable): |  | BTUs
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. | Connected to District Energy System? Yes/No:
|  | EUI target: |  | kBTU/SF/year
|  | Final EUI: |  | kBTU/SF/year
|  | Estimated annual energy savings from ECMs: |  | BTUs
| Energy Use Intensity (EUI) targets (EUIt): Design the building to perform better than the Washington State Clean Buildings Performance Standard (CBPS) EUIt for the building type and activities. Projects located in Seattle and not connected to the Seattle campus district energy system must also plan for compliance with the City of Seattle Building Performance Standard (BEPS) Greenhouse Gas Intensity (GHGi) target. Applicable to all Tier 1 projects. | Final GHGi (if applicable): |  | kgCO2e/SF/year
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS? | Estimated indoor water use (see LEED Indoor Water Use calculator): |  | Gallons
|  | Estimated indoor water use savings (see LEED Indoor Water Use calculator): |  | Gallons
|  | Indoor water savings over baseline (see LEED Indoor Water Use calculator): |  | %
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. | Water Use Intensity: | #DIV/0! | Gallons/SF
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. | Total energy savings from water savings: | 0 | kWh
EMBODIED CARBON |  | If EC3 was not used, list applicable materials used on the project and the actual kgCO2e per declared unit :
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include new or alterations to existing building envelope? | Bird Friendly Design Guidelines followed?: Yes/No
HEALTH AND WELL-BEING | New construction projects must include showers and changing facilities. Major renovation projects evaluate options to provide showers and changing facilities. Applicable to all Tier 1 projects. | Showers/changing facilites provided on project?: Yes/No
EQUITY | Lactation facilities - New buildings and major renovation projects should include lactation facilities that support infant feeding, nursing, and pumping of breast milk for building occupants. Applicable to all Tier 1 projects. | New/improved lacation facilities included?: Yes/No
| UW Gender Inclusive Restroom Design Guidelines policy - does the building include new or renovated restrooms ? | All Gender Restrooms provided?: Yes/No
- insulation
- metal panel cladding (not insulated)
- membrane roofing
- flat glass (not IGUs)
- gypsum board (lightweight, type X, and glass mat)
- resilient vinyl or rubber flooring
Review GBS for link/requirements for embodied carbon limits.

## Step 4 Summary Tier 2a
Summary
Instructions: Enter answers as applicable, confirm the units. Shaded cells auto-fill |  | 0
|  |  | Enter Answer | Units
PROCESS | Follow UW GBS Process - applicable to all Tier 1 projects.
LIFE CYCLE COST ANALYSIS | Apply UW LCCA requirements
State ELCCA
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 1 projects.
PROJECT INFO |  | Gross Floor Area (GFA): |  | SF
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? | Use of fossil fuels on the project? Yes/No:
|  | Estimated annual fossil fuel use (if applicable): |  | BTUs
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. | Connected to District Energy System? Yes/No:
|  | EUI target: |  | kBTU/SF/year
|  | Final EUI: |  | kBTU/SF/year
| Energy Use Intensity (EUI) targets (EUIt): Design the building to perform better than the Washington State Clean Buildings Performance Standard (CBPS) EUIt for the building type and activities. Projects located in Seattle and not connected to the Seattle campus district energy system must also plan for compliance with the City of Seattle Building Performance Standard (BEPS) Greenhouse Gas Intensity (GHGi) target. Applicable to all Tier 1 projects. | Final GHGi (if applicable): |  | kgCO2e/SF/year
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS? | Estimated indoor water use (see LEED Indoor Water Use calculator): |  | Gallons
|  | Estimated indoor water use savings (see LEED Indoor Water Use calculator): |  | Gallons
|  | Indoor water savings over baseline (see LEED Indoor Water Use calculator): |  | %
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. | Water Use Intensity: | #DIV/0! | Gallons/SF
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. | Total energy savings from water savings: | 0 | kWh
EMBODIED CARBON | Product embodied carbon limits: For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. | Did all of the materials meet the CLF material baseline? (Yes/No):
|  | Total embodied carbon (A1 to A4) of building as constructed (EC3): |  | kgCO2e/m2
RATING SYSTEM | Earn LEED v4 NC Gold certification including required credits in the UW LEED scorecard, and one innovation or pilot credit from the preferred list. Applicable to all Tier 1 projects. | Final LEED scoring points:
Final LEED certification level:
| Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 1 projects. | Name of Fitwel v3 credit documented:
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include new or alterations to existing building envelope? | Bird Friendly Design Guidelines followed?: Yes/No
HEALTH AND WELL-BEING | New construction projects must include showers and changing facilities. Major renovation projects evaluate options to provide showers and changing facilities. Applicable to all Tier 1 projects. | Showers/changing facilites provided on project?: Yes/No
EQUITY | Lactation facilities - New buildings and major renovation projects should include lactation facilities that support infant feeding, nursing, and pumping of breast milk for building occupants. Applicable to all Tier 1 projects. | New/improved lacation facilities included?: Yes/No
| UW Gender Inclusive Restroom Design Guidelines policy - does the building include new or renovated restrooms ? | All Gender Restrooms provided?: Yes/No
LEED Stats |  | Energy performance savings (indicate metric used):
| - aluminum | Final C&D waste diversion: |  | %
- insulation
- metal panel cladding (not insulated)
- membrane roofing
- flat glass (not IGUs)
- gypsum board (lightweight, type X, and glass mat)
- resilient vinyl or rubber flooring
Review GBS for link/requirements for embodied carbon limits.

## Step 4 Summary Tier 1
Summary
Instructions: Enter answers as applicable, confirm the units. Shaded cells auto-fill |  | 0
|  |  | Enter Answer | Units
PROCESS | Follow UW GBS Process - applicable to all Tier 1 projects.
LIFE CYCLE COST ANALYSIS | Apply UW LCCA requirements
State ELCCA
DESIGN STANDARDS | Comply with the UW Facility Design Standard and/or applicable similar standards for other campuses and departments. Applicable to all Tier 1 projects.
PROJECT INFO |  | Gross Floor Area (GFA): |  | SF
ENERGY & CLIMATE | No fossil fuels - Are there existing fossil fuels uses in the project or unique needs that require adding fossil fueled equipment? | Use of fossil fuels on the project? Yes/No:
|  | Estimated annual fossil fuel use (if applicable): |  | BTUs
| Connect to district energy systems - Applicable if district heating and/or cooling is available for the project but it is not currently connected and the project scope involves connecting a building to an energy source. | Connected to District Energy System? Yes/No:
|  | EUI target: |  | kBTU/SF/year
|  | Final EUI: |  | kBTU/SF/year
| Energy Use Intensity (EUI) targets (EUIt): Design the building to perform better than the Washington State Clean Buildings Performance Standard (CBPS) EUIt for the building type and activities. Projects located in Seattle and not connected to the Seattle campus district energy system must also plan for compliance with the City of Seattle Building Performance Standard (BEPS) Greenhouse Gas Intensity (GHGi) target. Applicable to all Tier 1 projects. | Final GHGi (if applicable): |  | kgCO2e/SF/year
WATER | Fixture, appliance, and equipment efficiency - does project have water consuming components with efficiency standards in the GBS? | Estimated indoor water use (see LEED Indoor Water Use calculator): |  | Gallons
|  | Estimated indoor water use savings (see LEED Indoor Water Use calculator): |  | Gallons
|  | Indoor water savings over baseline (see LEED Indoor Water Use calculator): |  | %
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. | Water Use Intensity: | #DIV/0! | Gallons/SF
| Water efficiency target - Does the project include new or renovated bathrooms? Achieve at least a 25% reduction from LEED BD+C v4 baseline unless existing plumbing will not support lower flow. | Total energy savings from water savings: | 0 | kWh
EMBODIED CARBON | Product embodied carbon limits: For all materials used on the project and listed in the Carbon Leadership Forum’s Material Baselines Report, select products that do not exceed the specified amount of kgCO2e per declared unit. | Did all of the materials meet the CLF material baseline? (Yes/No):
|  | Total embodied carbon (A1 to A4) of baseline building as designed (WBLCA): |  | kgCO2e/m2
| Is this project a major renovation of an existing building? If so, estimate the embodied carbon impact of the materials required to build a new, similar building using EC3 and the LEED pilot credit (MRpc132) methodology. | Total embodied carbon (A1 to A4) of proposed building as designed (WBLCA): |  | kgCO2e/m2
|  | Is the targeted embodied carbon below the limit of 500 kgCO2e/m2? (Yes/No): | No | kgCO2e/m2
|  | Total embodied carbon (A1 to A4) of building as constructed (EC3): |  | kgCO2e/m2
| At the end of the project, report as-built embodied carbon of actual new construction materials using the EC3 tool and following the LEED pilot credit for Procurement of Low-Carbon Construction Materials (MRpc132). Applicable to all Tier 1 projects. | For major renovation, total embodied carbon (A1 to A4) of new building (EC3): |  | kgCO2e/m2
RATING SYSTEM | Earn LEED v4 NC Gold certification including required credits in the UW LEED scorecard, and one innovation or pilot credit from the preferred list. Applicable to all Tier 1 projects. | Final LEED scoring points:
Final LEED certification level:
| Pilot at least one Fitwel v3 credit that addresses resiliency, ecology, experience of place, health and well-being, or diversity, equity, and inclusion and is appropriate for the project. Applicable to all Tier 1 projects. | Name of Fitwel v3 credit documented:
ECOLOGY | UW Bird-Friendly Design Guidelines - does this project include new or alterations to existing building envelope? | Bird Friendly Design Guidelines followed?: Yes/No
HEALTH AND WELL-BEING | New construction projects must include showers and changing facilities. Major renovation projects evaluate options to provide showers and changing facilities. Applicable to all Tier 1 projects. | Showers/changing facilites provided on project?: Yes/No
EQUITY | Lactation facilities - New buildings and major renovation projects should include lactation facilities that support infant feeding, nursing, and pumping of breast milk for building occupants. Applicable to all Tier 1 projects. | New/improved lacation facilities included?: Yes/No
| UW Gender Inclusive Restroom Design Guidelines policy - does the building include new or renovated restrooms ? | All Gender Restrooms provided?: Yes/No
LEED Stats: |  | Outdoor water use savings (see LEED Outdoor Water Use Calculator): |  | Gallons
|  | Total water use savings: | 0 | Gallons
Energy performance savings (indicate metric used):
| - aluminum | Final C&D waste diversion: |  | %
- insulation
- metal panel cladding (not insulated)
- membrane roofing
- flat glass (not IGUs)
- gypsum board (lightweight, type X, and glass mat)
- resilient vinyl or rubber flooring
Review GBS for link/requirements for embodied carbon limits.